Cowichan Watershed Society

DRAFT WORK PLAN

2017 Year End Review

Tom Rutherford

Jill Thompson

29/01/2018

DRAFT 2017 Work plan – Cowichan Watershed Society

Priorities

- Green = highest immediate priority – funding secured

- Orange = medium priority – if funding secured

- Pink = lower priority OR unfunded

Funding Sources

OPS = Operations Budget contributed by the CVRD and Cowichan Tribes

REFBC = Grant 2014-2018 from the Real Estate Foundation of BC for local governance readiness

Legacy Fund = Grant(s) from BC Freshwater Legacy Fund for local governance work

Sustainable Funding for Watershed Governance Initiative = Grant(s) to explore sustainable funding mechanisms for local water(shed) governance

Eco Action = grants from Environment Canada for citizen engagement on climate (water quality, quantity)

Summer Jobs = partial grants for summer students from Government of Canada (cover min. wage only)

Sponsors = local business donors and sponsorships

Staff

Tom = Tom Rutherford, Executive Director

Jill = Jill Thompson, Community Coordinator

- General Operations

|  | Target/ Project | Activities | Lead | Update |
| --- | --- | --- | --- | --- |
| 1 | Board Coordination and Support | Organize and/or serve as a resource for Board/Society/Technical Advisory Committee, selected Working Groups and related meetings | Tom / Jill | All priority General Ops. Activities Carried out Successfully with Exception of 5 year Review of targets Regular Attendance at Partnership Meetings in Cowichan Valley |
| 1 |  | Liaise with Board/TAC members, Special Advisors/Government staff/ and stakeholders in the interests of the CWB |  |  |
| 1 |  | Review policy documents relevant to the watershed and prepare briefings materials, position papers, letters of support, speaking notes etc. |  |  |
| 1 | Financial Mgmt | Monitor/manage budget |  |  |
| 1 |  | Pursue funding for ops and projects |  |  |
| 1 | TAC and Working Group Coordination | Implement 5 year review of targets |  |  |
| 1 |  | Support and coordinate Target Working Groups |  |  |
| 1 | Build and Support Partnerships | Maintain relationships with stakeholders –particularly stewardship groups within the watershed |  |  |
| 2 |  | Attend Agricultural Commission, Stewardship Roundtable, Cowichan Lake and River Stewardship etc. meetings as time permits. |  |  |
| 3 | Other | Other initiatives as opportunities arise and based on Board direction and available funds. |  |  |
| 3 |  | Pursue opportunities that may benefit the CWB and or the watershed |  |  |
| 1 | : Digital Presence | Website improvements | Jill, Arthur Caldicott | Challenges with updating website. |
| 1 |  | Facebook presence – CWB, Water Woman, partner sites. | Jill | Ongoing Facebook Presence |
| 1 | Media | Periodic articles, E-Newsletter, radio interviews | Jill, Tom, comms contractor | Articles in local media outlets and E-Newsletter |
| 2 | Community Engagement Events | River Cleanup- Participation in Upper River cleanup and participation, support organization and promotion in the Lower River Clean Up with CLRSS and Cowichan Tribes | Jill | Participation in Upper River Clean up Organization and implementation of best attended lower river clean up |

- Local Governance

|  | Target/Project | Activities | Lead | Update |
| --- | --- | --- | --- | --- |
| 2 | CWB Organizational Structure | Work with Key partners to more clearly define relationship between CWB,CVRD and Cowichan Tribes and role of CWB in local water(shed) governance moving forward | Tom | CWB CO-Governance Conversations workshop series funded by BCFWLI |
| 2 | BC Water Sustainability Act Tools and Initiatives | Work with Province of BC to explore advisory function, critical flows and drought management as defined under the WSA | Tom, Board Committee, Flows Working Group | Regular Meetings with FNLRORD Management Team – Progress on Koksiah Critical Flow Thresholds |
| 1 | Sustainable Watershed Governance Funding | Explore mechanisms for accessing sustainable funding for local water and watershed governance in the Cowichan valley | Cowichan Team(L. George, B. Carruthers, D. Slade, Tom, Jill | CVRD Working towards creation of Water/watershed stewardship service Lydia Hwitsum working towards identifying sustainable funding options for Cowichan tribes |
| 2 | Communications | Communications support for Local Governance | Jill | Ongoing |

- Technical Working Groups

|  | Target/Project | Activities | Lead | Update |
| --- | --- | --- | --- | --- |
|  | FLOW TARGET |  |  |  |
| 1 | Target - Successfully Increase the Probability of Adequate Summer Flows in the Cowichan River | Work with primary partners (Cowichan Tribes, CVRD, Catalyst Paper) to develop and implement strategic plan to increase storage capacity in Cowichan Lake | Tom Partners/ fish-flows WG/ Possible contract | Water Use Planning Process |
| 1 |  | Structured decision making process to develop science based target and minimum fish flows | Fish-flows WG | Complete – Foundational Document informing WUP ARTSG |
| 1 |  | Broadly scoped SD process to define Cowichan flow targets for cultural, recreational, agricultural and industrial interests | CVRD | Water Use Planning Process |
| 1 |  | Build knowledge base and support among community stakeholders | Tom, Jill, Contract | One on one conversations with Lake Front Property Owners |
| 1 |  | Public communications regarding drought management. Monitoring and reporting to public and province | Tom/Jill/ Fish-flows WG |  |
| 2 | Project - Building Knowledge re implications of climate change and land use management on health of lake and river | Organize Working forest tour for community leaders and decision makers to increase knowledge of current practices and continued dialogue around land use in the Cowichan Valley | Tom/ Riparian WG | Completed May 2017 |
|  | Ad Hoc flows committee | Represent CWB perspective on weekly Catalyst Ad Hoc Flow calls | Tom | Participated in Calls Successful 2017 Season |
|  | Project - Cowichan Watershed Water Budget and relationships between Surface and Ground water | Assist in identifying remaining knowledge gaps regarding groundwater and groundwater/surface water issues. |  | Meetings with Pat Lapcevic regarding reporting out on completed work |
| 1 | Surface Water Quality Monitoring 2016-2018 | Ongoing collaboration with others regarding continued standard monitoring of key sites: Koksilah River, Cowichan Bay bench and Cowichan River/Fish Gut alley; marine – e-coli sampling; spot checking farms; microbial source tracking at freshwater and marine sites Outreach to farming community – livestock producers: • communication materials • Farm visits/workshops | Water Quality WG MOE CCLT | Water quality sampling completed Nov. 2017, report due Feb. 2018. Agricultural outreach after results completed |
| 2 | Cowichan Bay Vessel Operators Restriction Implementation | Ongoing collaboration to fully implement VORR in Cowichan Bay to protect sensitive habitats Fund raise, purchase and install buoys Outreach education initiative Compliance program (CT, DFO, RCMP) | Water Quality/ Est. Health WG | First Buoys installed (CVRD Parks lead) Proposal for additional funding to be submitted Feb. 2018 |
| 2 | Clam Garden | Planning for clam garden pilot in Cowichan Bay Funding Tech support Site survey Traditional Knowledge Eng/feasibility Permitting | Water Quality Est. Health WG | No Progress in 2017 Kim Lagimodiere to Lead efforts in 201 |
| 3 | Groundwater Quality Monitoring | Collaborate with others and assess results of completed study coordinated by MFLNRO, identify ongoing monitoring requirements and help seek funds as appropriate. | Tom | Report not yet released |
| 1 | Restore 10% of impacted shoreline habitat by 2021 | Continue to work with Riparian WG to coordinate and support Riparian restoration works including Prioritization (restoration & acquisition) Standardized Monitoring Development of riparian outreach/Education messaging Inventory of current riparian habitats, issues and opportunities Invasive Plant Issues and Strategies | Riparian WG | Major CRF funded 5 year riparian restoration program for Cowichan Lake, river and Koksilah |
| 2 | Formal protection of 50% of remaining shoreline | Continue to work with local Stewardship Groups, the CVRD, Cowichan Tribes and national/provincial scale conservation organizations to acquire the Shaw Creek Properties | Tom | No Progress with Land Acquisition |
| 3 |  | Work with Working Group to set priorities for acquisition or alternate forms of protection | Riparian WG | Ongoing |
| 3 |  | Meet with TimberWest senior management to discuss targets and possible mutually beneficial means of formally protecting riparian habitats. | Tom | After forestry tour |
| 2 | Chinook | Support Chinook restoration initiative and development of Chinook target utilizing the Flows and Fish Working Group as a forum. | Fish-flows WG | Support to DFO Chinook rebuilding Framework |
| 3 | Steelhead | Encourage MOE/BCCF to monitor and report status to Board. Prepare letters of support for BCCF as required. | Fish-flows WG | Ongoing |
| 2 | Residential Water Conservation Challenge 2014-2018 | Water Challenge reporting and analysis, and public announcement of results | Jill, David S., Water Suppliers | Completed and extended |
| 2 | Encourage water conservation by major water users | Organize attend meeting with Catalyst Management to continue discussion on water conservation within its operations – (and how to assist with getting conservation initiative messaging out) as well as strategic planning related to increased storage | Tom, Jill, David | May |
| 3 | Public Engagement | Water conservation and awareness outreach program, educational workshops. | Jill, youth | May – Sept |
| 1 | Coordination and gap analysis | Working Group to carry out gap analysis to determine potential areas of engagement required to meet Watershed IQ targets | Watershed IQ working group | In progress, support from Social Planning Cowichan |
| 2 | Speaker Series | Organize/promote Watershed Speaker Series With VIU | Jill, Tom | ONGOING |
| 3 | Watershed Field Trips |  | Tom | Ongoing as funding permits |
| 2 | Door to Door Survey | Analysis of water knowledge survey | Jill, contractor | Not yet Completed |