Cowichan Watershed Society

DRAFT WORK PLAN

2018

Tom Rutherford

Jill Thompson

1/29/2018

DRAFT 2018 Work plan – Cowichan Watershed Society

Priorities

- Green = highest immediate priority – funding secured

- Orange = medium priority – if funding secured

- Pink = lower priority OR unfunded

Funding Sources

OPS = Operations Budget contributed by the CVRD and Cowichan Tribes

REFBC = Grant 2014-2018 from the Real Estate Foundation of BC for local governance readiness

Legacy Fund = Grant(s) from BC Freshwater Legacy Fund for local governance work

Sustainable Funding for Watershed Governance Initiative = Grant(s) to explore sustainable funding mechanisms for local water(shed) governance

Eco Action = grants from Environment Canada for citizen engagement on climate (water quality, quantity)

Summer Jobs = partial grants for summer students from Government of Canada (cover min. wage only)

Sponsors = local business donors and sponsorships

Staff

Tom = Tom Rutherford, Executive Director

Jill = Jill Thompson, Project Coordinator

- General Operations

|  | Target/ Project | Activities | Lead | Timeframes (2018) | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  | GENERAL OPERATIONS |
| 1 | Board Coordination and Support | Organize and/or serve as a resource for Board/Society/Technical Advisory Committee, selected Working Groups and related meetings | Tom / Jill | Ongoing | OPS |
| 1 |  | Liaise with Board/TAC members, Special Advisors/Government staff/ and stakeholders in the interests of the CWB |  |  |  |
| 1 |  | Review policy documents relevant to the watershed and prepare briefings materials, position papers, letters of support, speaking notes etc. |  |  |  |
| 1 |  | Support Co-chairs/Ministers Meetings |  |  |  |
| 1 | Strategic Planning | Update CWB workplan |  |  |  |
| 1 |  | Work with CVRD and Cowichan Tribes to update CBWMP implementation plan |  |  |  |
| 1 |  | Develop Work plans, hire and supervise contract/student support as needed |  |  |  |
| 1 | Financial Mgmt. | Monitor/manage budget |  |  |  |
| 1 |  | Pursue funding for ops and projects |  |  |  |
| 1 | TAC and Working Group Coordination | Implement 5-year review of targets |  |  |  |
| 1 |  | Support and coordinate and recruit funding TAC and Target Working Groups |  |  |  |
| 1 | Build and Support Partnerships | Maintain relationships with stakeholders –particularly stewardship groups within the watershed |  |  |  |
| 2 |  | Attend Agricultural Commission, Stewardship Roundtable, Cowichan Lake and River Stewardship etc. meetings as time permits. |  |  |  |
| 3 | Other | Other initiatives as opportunities arise and based on Board direction and available funds. |  |  |  |
| 3 |  | Pursue opportunities that may benefit the CWB and or the watershed |  |  |  |
|  | COMMUNICATIONS – Building Organizational Profile and community engagement |
| 1 | : Digital Presence | Website improvements | Jill, Arthur Caldicott | Ongoing | REFBC |
| 1 |  | Facebook presence – CWB, Superheroes, partner sites. | Jill | Ongoing | OPS, Legacy Fund (Pending) |
| 1 | Media | Periodic articles, E-Newsletter, radio interviews | Jill, Tom, comms contract | Ongoing | OPS, Legacy Fund (Pending) |
| 2 | Community Engagement Events | River Cleanup- Participation in Upper River cleanup and participation, support organization and promotion in the Lower River Clean Up with CLRSS and Cowichan Tribes | Jill | August | Sponsors |

- Local Governance

|  | Target/Project | Activities | Lead | Timeframes (2018) | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  | LOCAL GOVERNANCE |
| 1 | Sustainable Watershed Governance Funding | Explore mechanisms for accessing sustainable funding for local water and watershed governance in the Cowichan valley | (L. Hwitsum, B. Carruthers, D. Slade, Tom, Jill | Ongoing | SFWGI |
| 1 | Sustainable Watershed Governance Funding | Support CVRD work to create Water/Watershed stewardship service | Tom, Jill | Jan. – Oct. | SFWGI (Pending) |
| 1 | CWB Organizational Structure | Complete second and third Cowichan Co-governance Conversations Workshops | Tom | Jan. - April 2018 | Legacy Fund |
| 1 |  | Update CWB Governance Manual accordingly and present to CWB. Cowichan Tribes and CVRD for support and ratification | Tom/Jill | Jan. - April 2018 | Legacy Fund |
| 1 |  | Complete Options Paper outlining outcomes of Workshop Series in terms of an expanded role for CWB in terms of partnership with Prov. of BC to develop WSA tools (and beyond) | Tom/Jill, Special Advisors | April - August 2018 | Legacy Fund |
| 1 | BC Water Sustainability Act Tools and Initiatives | Work with Province of BC to explore partnership to develop WSA tools that will result in positive outcomes for Cowichan Watershed (eg. WSP, Critical Flows, Drought Management Plan, etc.) | Tom, Jill | June – Dec. 2018 | Legacy Fund |
| 2 | Communications | Communications support for Local Governance | Jill | Ongoing | Legacy Fund (Pending) |

- Technical Working Groups

|  | Target/Project | Activities | Lead | Timeframe (2018) | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  | FLOW TARGET |  |  |  |  |
|  |  | Participate in Cowichan WUP process (Steering Committee, ARTSG, PAG) as advocate for sustainable ecological flows | Tom | Jan. - June | OPS |
| 1 | Target - Successfully Increase the Probability of Adequate Summer Flows in the Cowichan River | Work with primary partners (Cowichan Tribes, CVRD, Catalyst Paper) to develop and implement strategic plan to increase storage capacity in Cowichan Lake | Tom Partners/ fish-flows WG/ Possible contract | March- Dec. | OPS/ REFBC |
| 1 |  | Encourage, Facilitate and support discussions to identify Conservation license holder for Cowichan river | Tom | Feb.-Dec. | OPS/ REFBC |
| 1 |  | Build knowledge base and support among community stakeholders | Tom, Jill, Contract | To March 2018 | REFBC |
| 1 |  | Public communications regarding drought management. Monitoring and reporting to public and province | Tom/Jill/ Fish-flows WG | To March 2018 | REFBC |
| 1 | Ad Hoc flows committee | Represent CWB perspective on weekly Catalyst Ad Hoc Flow calls | Tom | April-Nov. | OPS/ REFBC |
| 2 | Project - Building Knowledge re implications of climate change and land use management on health of lake and river | •Support Cowichan Watershed forest hydrology research | Tom/ Riparian WG | Feb. – Dec. | REFBC/ OPS |
|  | Project - Cowichan Watershed Water Budget and relationships between Surface and Ground water | Assist in identifying remaining knowledge gaps regarding groundwater and groundwater/surface water issues. |  | Based on assessment of current project | Seek funds as appropriate. |
|  | WATER QUALITY /PUBLIC HEALTH/SHELLFISH TARGETS |
| 1 | Surface Water Quality Monitoring 2016-2018 | Ongoing collaboration with others regarding continued standard monitoring of key sites Work with MOE to update water objectives for Cowichan watershed and report out on 2017 WQ sampling program Outreach to farming community – livestock producers: • communication materials • Farm visits/workshops | Water Quality WG MOE CCLT SMWS CT | To March 2018 | REFBC |
| 1 | Coastal Restoration Fund | Participate in Cowichan CRF steering committee Support Cowichan CRF OPS | Tom | Jan. – Dec. | OPS |
| 2 | Cowichan Bay Vessel Operators Restriction Implementation | Ongoing collaboration to fully implement VORR in Cowichan Bay to protect sensitive habitats Fund raise, purchase and install buoys Outreach education initiative Compliance program (CT, DFO, RCMP) | Water Quality/ Est. Health WG | March-Dec. | OPS/ Partner Funding |
| 2 | Clam Garden | Planning for clam garden pilot in Cowichan Bay Funding Tech support Site survey Traditional Knowledge Eng./feasibility Permitting | Water Quality Est. Health WG | Ongoing | OPS/ Partner Funding |
| 3 | Groundwater Quality Monitoring | Collaborate with others and assess results of completed study coordinated by MFLNRO, identify ongoing monitoring requirements and help seek funds as appropriate. | Tom | Ongoing | Seek funds as appropriate. |
|  | RIPARIAN TARGETS |
| 1 | Restore 10% of impacted shoreline habitat by 2021 | Continue to work with Riparian WG to coordinate and support Riparian restoration works including Prioritization (restoration & acquisition) Standardized Monitoring Development of riparian outreach/Education messaging Inventory of current riparian habitats, issues and opportunities Invasive Plant Issues and Strategies | Riparian WG | Ongoing | OPS/ various funding partners |
| 2 | Formal protection of 50% of remaining shoreline | Continue to work with local Stewardship Groups, the CVRD, Cowichan Tribes and national/provincial scale conservation organizations to acquire the Shaw Creek Properties a | Tom | Ongoing until acquired | OPS |
| 2 |  | Development of Watershed wide knotweed management strategy | Riparia WG | Ongoing | OPS |
| 3 |  | Work with Working Group to set priorities for acquisition or alternate forms of protection | Riparian WG | Ongoing | OPS |
| 3 |  | Meet with TW senior management to discuss targets and possible mutually beneficial means of formally protecting riparian habitats. | Tom | After forestry tour | OPS |
|  | FISH SUSTAINABILITY TARGET |
| 2 | Chinook | Support Chinook restoration initiative and development of Chinook target utilizing the Flows and Fish Working Group as a forum. | Fish-flows WG | January -Ongoing | OPS |
| 2 | Coho/Chinook | Obtain 3rd party resources to ground truth historic side channel connectivity data on Cowichan river | Fish Flows WG |  | OPS |
| 3 | Steelhead | Encourage MOE/BCCF to monitor and report status to Board. Prepare letters of support for BCCF as required. | Fish-flows WG | Ongoing | OPS |
|  | WATER CONSERVATION TARGET |
| 2 | Residential Water Conservation Challenge 2014-2018 | Water Challenge reporting and analysis, and public announcement of results | Jill, David S., Water Suppliers | Ongoing | OPS, EcoAction Pending |
| 2 | Encourage water conservation by major water users | Organize attend meeting with Catalyst Management to continue discussion on water conservation within its operations – (and how to assist with getting conservation initiative messaging out) as well as strategic planning related to increased storage | Tom, Jill, David | May | OPS |
| 3 | Public Engagement | Water conservation and awareness outreach program, educational workshops. | Jill, youth | May – Sept | Sponsors Summer Jobs, EcoAction |
|  | WATERSHED EDUCATION/IQ |
| 1 | Coordination and gap analysis | Working Group to complete gap analysis to determine potential areas of engagement required to meet Watershed IQ targets | Watershed IQ working group | Jan. - June | OPS |
| 1 | Speaker Series | Organize/promote Watershed Speaker Series With VIU | Jill, Tom | 9 months / yr. | REFBC, Sponsors |
| 2 | Watershed Field Trip | Carry out 1 strategic watershed field trip spring 2018 | Tom, Rodger | Feb.-May | REFBC |
| 2 | Door to Door Survey | Analysis of water knowledge survey | Jill, contractor | Feb-April | REFBC |
| 2 | Education programming | Obtain resources to enable salmon-oriented field trips for cowichan valley schools fall 2018 | Watershed IQ working Group | Mar. – Nov. | OPS |